## Sheet1
Prototyping Schedule
Subsytem | Mid-December | Late-December | Early-January | Mid-January | Late-January | Early-February | Mid-February | Late-February | Early-March | Mid-March | Late-March | Early-April | Mid-April | Late-April
MPU-6050
SD Card Reader
Motor
Linear Actuator
GoPro
Full-scale Integration
Fabrication Schedule
End Effector PCB
Main PCB
GoPro
Testing Schedule
Subsystem Testing
Integrated Subsystem
MCU Testing
Components Overheating
Power Consumption
Conformal Coating Testing
Full Mission Test
| To Do List: | Push button to make linear actuator work |  |  |  | 2019-02-15
|  | Push button to make Motor go out and in |  |  |  | 2019-02-15 |  |  |  | March 17th | Spring Break and also important deadline
|  | Read data through the slip ring - communication between arduinos need to be |  |  |  | 2019-02-15 |  |  |  | Mid February |  | They want to see full prototyping
50% - 75% project finished
|  | Full integration must be done (things can be on breadboard still) |  |  |  | 2019-03-25
|  | 100% complete | PCBS are in, power supply can be hooked up to it |  |  | 2019-04-30
|  | Integration |  |  |  | 2019-06-17